## Duration
Main | Duration | Start Date | End Date
Browser | 3 | 2018-09-06 | 2018-09-10
Files | 1 | 2018-09-11 | 2018-09-11
Files Reader | 2 | 2018-09-12 | 2018-09-13
File List | 1 | 2018-09-17 | 2018-09-17
File Info | 1 | 2018-09-18 | 2018-09-18
File Favourite | 1 | 2018-09-19 | 2018-09-19
Reading Mode | 1 | 2018-09-20 | 2018-09-20
Audio Setting | 1 | 2018-09-21 | 2018-09-21
Translation | 2 | 2018-09-24 | 2018-09-25
Home Page Changes | 1 | 2018-09-26 | 2018-09-26
Setting | 2 | 2018-09-27 | 2018-09-28
Cloud Storage (Upload/Download) | 2 | 2018-10-01 | 2018-10-03
Tutorial Pages to Video | 1 | 2018-10-04 | 2018-10-04
Free Ebook Api | 1 | 2018-10-05 | 2018-10-05
20

## Task
Task
All types of text file should be readable in app, example epub, doc, etc.
Change 2 Tab from pdf to Doc/ files.
Create a new Logo for Browser : Shoolin
Recreate Broswer Page of Tab 1. (Refer Yo Browser app )
Video should be playable in Browser.
Change for function of Speak icon of Browser with following options:
On Web Page their should be Home Icon which will navigate to Home page of Browser tab.
Browser should be showing options like Yo Browser App
Recent and most popular should be displayed liked Yo Browser App
Add on features: READ IT App should have options to change with Themes which will be in Setting of App with following options to change
Tab 2 should have to options to display list in List and Grid(with different type of files)
Browsing of images should be from gallery.
Tab 4 should show Keyboard, which is currently not showing currently for few devices.
Whenever tts speak, their should be Uniform player with different options(eReader App)
Options to create Audio files with will be displayed in Recent Audios.
Audio files creations of different langauges depending on selection.
Search should be working
Menu should change with side drawer options which contain user info and other setting options and grouping of some options like feedback, sharing, etc
Audio Setting page should be change with collapse options of main sections.
Language selection should contain list of all languages present on device.
Scanning of device options should be present in Settings and should scan for files with different types including epub, docs, etc.
Menu should be customized and should remove storage used and data usage.
Setting should also contain options to read files from drive, cloud storage with other options to upload and download file
Language selection and translation options should be their.
Their should be options to delete and share files from recent Images and Pdf file(doc files)
Their should be options to mark files as Favorite and all list Favorites should be displayed with the options present in menu/ setting.
Ocr text should be scrollable
Menu should be similar to menu of eReader App.
Camera should have ocr options even before click the image.
Add on features : Reading Mode of Files with Animation Flip Of page of files and auto reading.
Reading Mode should be light theme and should be playing files
File should be open from last page visited
Synchronization of setting and all data of app (Future Enhancement)
App Widget.
Item of list should be displayed qith curved corner and shadow